## GanttChart
GCPS Bus Monitoring System
Sam Bostian, Michael Rizig, Charlie McLarty, Brian Pruitt
Project Start: 8/12/24 | [5 empty] | August |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
[6 empty] | Plan |  |  | M1 |  |  |  | M2 |  | M3 |  | M4 |  |  |  |  | M5
TASK |  | ASSIGNED TO | PROGRESS | START | END | 18 | 25 | 1 | 8 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 1 | 8 | 19 | 22 | 2 | 9 | 11 | 12
Planning
Define goals and project scope |  | ALL | 100% | 2024-08-12 | 2024-08-15 | 2
Define timeline |  | Michael Rizig | 100% | 2024-08-15 | 2024-08-17 | 2 | 2
Set Milestone Dates |  | Sam Bostain | 100% | 2024-08-17 | 2024-08-21 |  | 2 | 2
Define Resources Required |  | Charlie McLarty | 100% | 2024-08-21 | 2024-08-24 |  | 2 | 3
Complete Project Plan |  | Michael Rizig | 100% | 2024-08-18 | 2024-09-01 |  |  | 4
Design
Define Dependencies |  | Sam Bostian | 0% | 2024-08-12 | 2024-08-31 | 2 | 2
Create SDD Document |  | Brian Pruitt | 0% | 2024-08-12 | 2024-08-28 | 2 | 2 | 2
Create SRS Documents |  | ALL | 0% | 2024-08-12 | 2024-08-31 | 2 | 3 | 2
Define Design Elements |  | ALL | 0% | 2024-08-12 | 2024-08-31 | 2 | 3 | 3
Compare/Analyze designs |  | Sam,Michael,Brian | 0% | 2024-08-12 | 2024-09-02 |  | 3 | 3
Complete SDD |  | Sam,Charlie,Brian | 0% | 2024-08-12 | 2024-09-02 |  | 4 | 4
Complete SRS |  | ALL | 0% | 2024-08-12 | 2024-09-02 |  | 4 | 4
Execution | [8 empty] | 2 | 2 | 2 | 2
Create Development Document |  | Michael Rizig | 0% | 2024-09-10 | 2024-09-30 |  |  |  | 3 | 2 | 2
Build Backend |  | Sam Bostian | 0% | 2024-09-10 | 2024-09-30 |  |  |  | 3 | 2 | 2 | 2
Establish Database |  | Charlie McLarty | 0% | 2024-09-15 | 2024-09-30 | [6 empty] | 2 | 2 | 2 | 2
Containerization |  | Sam,Michael | 0% | 2024-10-08 | 2024-10-29 | [9 empty] | 2 | 4
Create Presentation and Demo |  | Brian Pruitt | 0% | 2024-10-08 | 2024-10-29 | [8 empty] | 3 | 3 | 4
Test, evaluate, and debug |  | Charlie McLarty | 0% | 2024-09-20 | 2024-10-29 | [8 empty] | 3 | 3 | 4
Evaluation | [11 empty] | 2 | 2 | 2 | 4 | 3 |  | 2 | 2 | 2
Create Software Test Plan |  | Charlie McLarty | 0% | 2024-09-23 | 2024-11-27 | [12 empty] | 2 | 2 | 2
Clean up Prototype |  | Sam,Michael,Brian | 0% | 2024-09-28 | 2024-11-27 | [11 empty] | 2 | 2 | 2 | 2 |  |  |  | 2
Final debugging |  | Sam, Charlie | 0% | 2024-09-28 | 2024-11-27 | [12 empty] | 2 | 2 | 2 | 2 | 2 | 2
Complete Testing Documentation |  | Michael, Charlie | 0% | 2024-09-29 | 2024-11-27 | [15 empty] | 2 | 2 | 2
Complete Final report |  | ALL | 0% | 2024-09-17 | 2024-12-02 | [11 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[8 empty] | 2024-09-02 |  | 2024-09-16 |  |  |  | 2024-10-14 |  | 2024-10-28 |  |  | 2024-11-19 |  | 2024-12-02
Milestone | Description | Due Date | Completion
Plan | Project Plan Document | 2024-09-01 | TRUE
M1 | Initial Development | 2024-09-16 | FALSE
M2 | Database and Event Logging | 2024-10-14 | FALSE
M3 | Containerization | 2024-10-28 | FALSE
M4 | C-Day | 2024-11-19 | FALSE
M5 | Final Deliverable | 2024-12-02 | FALSE

## Mile Stone Key
Milestone | Description | Due Date | Completion
Plan | Project Plan Document | 2024-09-01 | TRUE
M1 | Initial Development | 2024-09-16 | FALSE
M2 | Database and Event Logging | 2024-10-14 | FALSE
M3 | Containerization | 2024-10-28 | FALSE
M4 | C-Day | 2024-11-19 | FALSE
M5 | Final Deliverable | 2024-12-02 | FALSE